## Retrospective
Sprint Retrospective Template
Sprint 14 · 3-16 March
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-retrospective-template/
Category | Observation | Votes | Discussion notes
Went well | Daily Scrums finished on time | 3
Went well | Pairing on the payments story | 4
To improve | Stories arrived in planning without acceptance criteria | 6 | Refine earlier
To improve | Build pipeline failed twice | 5
Ideas | Try a mid-Sprint refinement session | 4
Shout-outs | Thanks to Chen for fixing the test data | 2