## Instructions
Project Schedule Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-schedule-template/
Step | How to use this template
1 | List tasks in order, using your work breakdown structure as the source.
2 | Enter each task's start date and duration; the end date calculates automatically.
3 | Record predecessors to show task dependencies.
4 | Flag milestones and assign owners.
5 | Update % complete and status weekly, and adjust later dates when a predecessor slips.
Tip | Getting the most from it
1 | Find the longest chain of dependent tasks: that is your critical path.
2 | Add buffers to risky tasks.
3 | Baseline the schedule once approved.
4 | Show it as a Gantt chart for stakeholders.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Project Schedule Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-schedule-template/
Total rows with data
Owner | Count | Share
BA
Designer
Developers
PM
QA
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## Schedule
Project Schedule Template
End dates calculate from start date and duration (calendar days)
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-schedule-template/
ID | Task | Owner | Start | Duration (days) | End | Predecessor | % complete | Milestone? | Status
1 | Kick-off meeting | PM | 2026-03-02 | 1 |  |  | 100 | Yes | Done
2 | Gather requirements | BA | 2026-03-03 | 5 |  | 1 | 60 |  | In progress
3 | Design | Designer | 2026-03-10 | 8 |  | 2 | 0 |  | Not started
4 | Build | Developers | 2026-03-20 | 15 |  | 3 | 0 |  | Not started
5 | Test | QA | 2026-04-10 | 6 |  | 4 | 0 |  | Not started
6 | Launch | PM | 2026-04-20 | 1 |  | 5 | 0 | Yes | Not started

## Revision history
Project Schedule Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-schedule-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-16 |  | First version created from the template