## Instructions
Event Planning Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/event-planning-template/
Step | How to use this template
1 | Set the event's goal, audience, date and budget.
2 | Work back from the event date and assign each checklist task an owner.
3 | Book the venue and key vendors early.
4 | Track spend on the Budget tab as quotes and invoices arrive.
5 | After the event, gather feedback and record lessons learned.
Tip | Getting the most from it
1 | Book venues and speakers first: they set the date.
2 | Keep a 10% contingency.
3 | Have a run-of-show for the day.
4 | Use an event calendar for promotion.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Event Planning Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/event-planning-template/
Total rows with data
Owner | Count | Share
All
Event lead
Marketing
Ops
Programme lead
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## Checklist
Event Planning Template
Event: Customer summit · Date: 25 May 2026
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/event-planning-template/
Weeks before | Task | Owner | Due date | Status | Notes
12 | Set goals, audience and budget | Event lead | 2026-03-02 | Done
10 | Book venue | Event lead | 2026-03-16 | In progress | Two options
8 | Confirm speakers | Programme lead | 2026-03-30 | Not started
6 | Open registration | Marketing | 2026-04-13 | Not started
4 | Order catering and AV | Ops | 2026-04-27 | Not started
2 | Send joining instructions | Marketing | 2026-05-11 | Not started
0 | Run event and collect feedback | All | 2026-05-25 | Not started

## Budget
Event Planning Template
Track estimated versus actual spend
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/event-planning-template/
Item | Category | Estimated ($) | Actual ($) | Variance ($) | Vendor | Paid?
Venue hire | Venue | 6000 | 6000 |  | City Hall | Yes
Catering | Food | 4500 |  |  |  | No
AV and streaming | Tech | 3000 |  |  |  | No
Speaker travel | People | 2000 |  |  |  | No
Total

## Revision history
Event Planning Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/event-planning-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-26 |  | First version created from the template