## Instructions
Project Proposal Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-proposal-template/
Step | How to use this template
1 | Define the problem with evidence before proposing a solution.
2 | Describe the solution, objectives and scope, including exclusions.
3 | Fill in the Budget & timeline tab; contingency and total calculate automatically.
4 | State benefits and risks honestly.
5 | Write a one-paragraph summary and a clear ask, then share for approval.
Tip | Getting the most from it
1 | Lead with the decision-maker's priorities.
2 | Quantify benefits wherever possible.
3 | Keep it short; attach detail as appendices.
4 | Turn an approved proposal into a project charter.
Tabs: Revision history records changes to this file.

## Proposal
Project Proposal Template
Write the summary last
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-proposal-template/
Section | What to write | Your content
Title and summary | One paragraph: the problem, your solution and the ask.
Background / problem | What is wrong today and the evidence.
Proposed solution | What you will do and why this approach.
Objectives | Measurable outcomes (SMART).
Scope | In scope and out of scope.
Deliverables | What will be produced.
Approach and timeline | Phases and key milestones (see Budget & timeline tab).
Budget | Total cost and main cost lines.
Benefits | Financial and non-financial benefits; ROI if known.
Risks | Top risks and how you will manage them.
Team | Who will deliver and their roles.
Next steps / approval | Decision needed, by whom and by when.

## Budget & timeline
Project Proposal Template
Phases, dates and costs
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-proposal-template/
Phase / item | Start | End | Cost ($) | Notes
Discovery | 2026-04-01 | 2026-04-15 | 8000
Design | 2026-04-16 | 2026-05-08 | 15000
Build | 2026-05-11 | 2026-07-03 | 60000
Launch and training | 2026-07-06 | 2026-07-17 | 7000
Contingency (10%)
Total

## Revision history
Project Proposal Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-proposal-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-26 |  | First version created from the template