## Agile plan
Agile Project Plan Template
Plan epics by Sprint; adapt every Sprint Review
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/agile-project-plan-template/
Sprint | Dates | Sprint goal | Epics / features | Status
Sprint 1 | 2 – 13 Mar | Users can log in securely | Login, password reset | Done
Sprint 2 | 16 – 27 Mar | Users can view invoices | Invoices list, PDF download | In progress
Sprint 3 | 30 Mar – 10 Apr | Admins can manage users | User admin, exports | Not started
Sprint 4 | 13 – 24 Apr | Help content in-app | Help centre | Not started