## Instructions
Communication Plan Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/communication-plan-template/
Step | How to use this template
1 | List your stakeholders and what each needs to know (start from your stakeholder register).
2 | Define each communication's purpose and content.
3 | Choose the channel, frequency and format that suit each audience.
4 | Assign an owner for every communication.
5 | Agree how people give feedback, and review the plan at each phase.
Tip | Getting the most from it
1 | Tailor detail to the audience: executives want decisions and risks.
2 | Fewer, regular updates beat many ad hoc ones.
3 | Check people actually read them.
4 | Pair it with a RACI matrix.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Communication Plan Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/communication-plan-template/
Total rows with data
Owner | Count | Share
Comms lead
Marketing
Project manager
Sponsor
Team lead

## Communication plan
Communication Plan Template
Who needs what, when, how and from whom
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/communication-plan-template/
Communication | Audience | Purpose / content | Channel | Frequency | Owner | Format | Feedback route
Status report | Sponsor, steering group | Progress, RAG status, risks, decisions needed | Email + dashboard | Weekly | Project manager | 1-page report | Reply or steering meeting
Steering committee | Steering group | Decisions, escalations, budget | Meeting | Monthly | Sponsor | Slides | Minutes and actions
Team stand-up | Project team | Today's work and blockers | Video call | Daily | Team lead | 15-minute meeting | In the meeting
Stakeholder newsletter | Wider organisation | What's changing and when | Intranet | Monthly | Comms lead | Article | Comments
Go-live notice | Customers | New features and support | Email | Once | Marketing | Email | Support inbox

## Revision history
Communication Plan Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/communication-plan-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-17 |  | First version created from the template