## RAID log
RAID Log Template
Risks, Assumptions, Issues and Dependencies in one log
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/raid-log-template/
ID | Type | Description | Impact | Probability | Owner | Action / mitigation | Due | Status
R1 | Risk | Billing API may not be ready by 1 Feb | High | Medium | Tech lead | Weekly check-in with billing team; mock API ready | 2026-01-30 | In progress
A1 | Assumption | Support team available for UAT in March | Medium |  | PM | Confirm with support manager | 2026-02-05 | Not started
I1 | Issue | Test environment unstable | High |  | Ops lead | Rebuild environment; daily health check | 2026-01-20 | In progress
D1 | Dependency | Single sign-on from IT security project | High |  | PM | Track in IT security plan; agree date | 2026-02-27 | Not started