## Instructions
Risk Register Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/risk-register-template/
Step | How to use this template
1 | Identify risks with the team and write each as cause → event → effect.
2 | Score probability and impact from 1 to 5; the score calculates automatically.
3 | Sort by score and choose a response for the highest risks.
4 | Assign an owner and an action with a review date.
5 | Review the register regularly and record residual risk.
Tip | Getting the most from it
1 | Focus effort on the top 10 risks.
2 | Include opportunities as positive risks.
3 | Keep scoring definitions consistent.
4 | Link the register to your contingency plan.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Risk Register Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/risk-register-template/
Total rows with data
Category | Count | Share
Technical
Supply
People
Financial
Compliance
Schedule
External
Owner | Count | Share
Finance
PM
Procurement
Tech lead
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## Risk register
Risk Register Template
Score = probability x impact; 15-25 high, 8-14 medium, 1-7 low
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/risk-register-template/
ID | Risk (cause → event → effect) | Category | Probability (1-5) | Impact (1-5) | Score | Response | Action | Owner | Review date | Status
R1 | Supplier capacity is limited, so hardware may arrive late, delaying installation | Supply | 3 | 4 |  | Mitigate | Order early; identify second supplier | Procurement | 2026-02-02 | In progress
R2 | Key developer may leave, causing loss of knowledge and delay | People | 2 | 4 |  | Mitigate | Pair programming; document design | Tech lead | 2026-02-09 | In progress
R3 | New regulation may require extra data controls, increasing scope | Compliance | 2 | 3 |  | Accept | Monitor regulator updates monthly | PM | 2026-03-02 | Not started
R4 | Exchange-rate changes may raise licence costs | Financial | 3 | 2 |  | Transfer | Fix price in contract | Finance | 2026-02-16 | Done

## Revision history
Risk Register Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/risk-register-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-26 |  | First version created from the template