## Instructions
Marketing Campaign Plan Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/marketing-campaign-template/
Step | How to use this template
1 | Complete the Brief tab: goal, audience, message and offer.
2 | Plan tactics by channel with owners and dates.
3 | Allocate budget; the total calculates automatically.
4 | Set a KPI and target for each tactic.
5 | Track actual results weekly and shift budget to what works.
Tip | Getting the most from it
1 | One clear goal per campaign.
2 | Test messages before scaling spend.
3 | Use UTM links to track results.
4 | Plan content in the content calendar.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Marketing Campaign Plan Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/marketing-campaign-template/
Total rows with data
Owner | Count | Share
Ana
Ben
Chen
Dana
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## Campaign plan
Marketing Campaign Plan Template
Campaign: Spring launch · Goal: 500 qualified leads · Audience: operations managers
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/marketing-campaign-template/
Channel | Tactic | Owner | Start | End | Budget ($) | KPI | Target | Actual | Status
Email | 3-part nurture series | Ana | 2026-04-01 | 2026-04-21 | 500 | Click-through rate | 4% |  | Not started
Paid social | LinkedIn lead ads | Ben | 2026-04-01 | 2026-04-30 | 6000 | Leads | 300 |  | Not started
Content | Launch blog post and guide | Chen | 2026-03-30 | 2026-04-03 | 800 | Sessions | 5,000 |  | In progress
Events | Live webinar | Dana | 2026-04-15 | 2026-04-15 | 1200 | Registrants | 400 |  | Not started
Total

## Brief
Marketing Campaign Plan Template
Campaign brief
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/marketing-campaign-template/
Element | Details
Campaign name
Goal (SMART)
Target audience
Key message
Offer / call to action
Channels
Budget
Timeline
KPIs
Approver

## Revision history
Marketing Campaign Plan Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/marketing-campaign-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-16 |  | First version created from the template