## Instructions
Change Request Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/change-request-template/
Step | How to use this template
1 | Complete the form for each proposed change.
2 | Assess the impact on scope, time, cost, quality and risk.
3 | Log it in the change log and present it to the approver or change control board.
4 | Record the decision, approver and date.
5 | Update the plan, baseline and stakeholders when a change is approved.
Tip | Getting the most from it
1 | No change is too small to log.
2 | Agree approval thresholds in advance.
3 | Consider the combined impact of many small changes.
4 | See change control for the full process.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Change Request Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/change-request-template/
Total rows with data
Priority | Count | Share
High
Medium
Low
Decision | Count | Share
Pending
Approved
Rejected
Deferred

## Change log
Change Request Template
Log every change request and its decision
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/change-request-template/
CR # | Date raised | Raised by | Change description | Reason | Impact: scope | Impact: time (days) | Impact: cost ($) | Priority | Decision | Approved by | Decision date
CR-001 | 2026-02-10 | Sales lead | Add export to CSV on invoices page | Customer requests | Minor addition | 3 | 2400 | Medium | Approved | Sponsor | 2026-02-12
CR-002 | 2026-02-18 | Security | Add multi-factor login | Security policy | New feature | 10 | 9000 | High | Approved | Steering group | 2026-02-24
CR-003 | 2026-03-01 | Marketing | Change brand colours | Rebrand | Design rework | 5 | 3500 | Low | Deferred | Sponsor | 2026-03-04

## Change request form
Change Request Template
Use one form per change
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/change-request-template/
Field | Details
Change request number
Requested by / date
Description of change
Reason / benefit
Options considered
Impact on scope
Impact on schedule
Impact on cost
Impact on quality and risk
Recommendation
Decision and conditions
Approved by / date

## Revision history
Change Request Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/change-request-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-25 |  | First version created from the template