## Instructions
RAID Log Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/raid-log-template/
Step | How to use this template
1 | Add each item with a type and a clear description.
2 | Rate impact (and probability for risks).
3 | Assign an owner and agree an action with a due date.
4 | Review the log in every status meeting and update status.
5 | Escalate high-impact items to the sponsor and close items when resolved.
Tip | Getting the most from it
1 | Write risks as cause → event → effect.
2 | Validate assumptions early; unproven ones become risks.
3 | Convert risks that happen into issues.
4 | Keep closed items for lessons learned.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
RAID Log Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/raid-log-template/
Total rows with data
Type | Count | Share
Risk
Assumption
Issue
Dependency
Owner | Count | Share
Ops lead
PM
Tech lead
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## RAID log
RAID Log Template
Risks, Assumptions, Issues and Dependencies in one log
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/raid-log-template/
ID | Type | Description | Impact | Probability | Owner | Action / mitigation | Due | Status
R1 | Risk | Billing API may not be ready by 1 Feb | High | Medium | Tech lead | Weekly check-in with billing team; mock API ready | 2026-01-30 | In progress
A1 | Assumption | Support team available for UAT in March | Medium |  | PM | Confirm with support manager | 2026-02-05 | Not started
I1 | Issue | Test environment unstable | High |  | Ops lead | Rebuild environment; daily health check | 2026-01-20 | In progress
D1 | Dependency | Single sign-on from IT security project | High |  | PM | Track in IT security plan; agree date | 2026-02-27 | Not started

## Revision history
RAID Log Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/raid-log-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-25 |  | First version created from the template