## Instructions
Work Package Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/work-package-template/
Step | How to use this template
1 | Copy the WBS code and name from your WBS.
2 | Describe scope and deliverables.
3 | List tasks, then estimate effort and cost.
4 | Add dates, dependencies, risks and acceptance criteria.
5 | Agree it with the owner and approver before work starts.
Tip | Getting the most from it
1 | Keep work packages to a few weeks of effort.
2 | One owner per package.
3 | Acceptance criteria make progress objective.
4 | Roll up estimates to the cost estimate.
Tabs: Revision history records changes to this file.

## Work package
Work Package Template
One sheet per work package
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/work-package-template/
Field | Details
WBS code | 1.4.2
Work package name | Customer login and password reset
Owner | Tech lead
Description / scope | Build login, logout and password reset using single sign-on.
Deliverables | Working feature in test environment; unit tests; release notes.
Tasks | Design screens; build API; integrate SSO; write tests.
Effort estimate (days) | 12
Cost estimate ($) | 9,600
Start / finish | 2 Mar 2026 / 17 Mar 2026
Dependencies | SSO service (IT security project)
Acceptance criteria | All login test cases pass; security review approved.
Risks | SSO delay
Approved by / date

## Revision history
Work Package Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/work-package-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-25 |  | First version created from the template