## CPM
Critical Path Template
Enter ES from the forward pass and LS from the backward pass; float and critical flag calculate
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/critical-path-template/
Activity | Description | Duration | Predecessors | ES | EF | LS | LF | Total float | Critical?
A | Requirements | 4 |  | 0 |  | 0
B | Design | 3 | A | 4 |  | 4
C | Procure hardware | 2 | A | 4 |  | 8
D | Build | 5 | B | 7 |  | 7
E | Install hardware | 2 | C | 6 |  | 10
F | Test and launch | 2 | D, E | 12 |  | 12