## Campaign plan
Marketing Campaign Plan Template
Campaign: Spring launch · Goal: 500 qualified leads · Audience: operations managers
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/marketing-campaign-template/
Channel | Tactic | Owner | Start | End | Budget ($) | KPI | Target | Actual | Status
Email | 3-part nurture series | Ana | 2026-04-01 | 2026-04-21 | 500 | Click-through rate | 4% |  | Not started
Paid social | LinkedIn lead ads | Ben | 2026-04-01 | 2026-04-30 | 6000 | Leads | 300 |  | Not started
Content | Launch blog post and guide | Chen | 2026-03-30 | 2026-04-03 | 800 | Sessions | 5,000 |  | In progress
Events | Live webinar | Dana | 2026-04-15 | 2026-04-15 | 1200 | Registrants | 400 |  | Not started
Total

## Brief
Marketing Campaign Plan Template
Campaign brief
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/marketing-campaign-template/
Element | Details
Campaign name
Goal (SMART)
Target audience
Key message
Offer / call to action
Channels
Budget
Timeline
KPIs
Approver