## Instructions
Project Charter Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-charter-template/
Step | How to use this template
1 | Agree the purpose and objectives with the sponsor before writing anything else.
2 | Fill in scope and, just as importantly, what is out of scope.
3 | Add milestones, budget, top risks, assumptions and constraints.
4 | Name the sponsor and project manager and state the project manager's authority.
5 | Review it with key stakeholders, then get the sponsor's signature.
6 | Store the signed charter with the project management plan and revisit it at major milestones.
Tip | Getting the most from it
1 | Keep it to two pages; detail belongs in the project plan.
2 | Write objectives you can measure at the end.
3 | List exclusions to prevent scope creep.
4 | Do not start detailed planning until it is signed.
Tabs: Revision history records changes to this file.

## Project charter
Project Charter Template
Complete each section and get the sponsor's sign-off
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-charter-template/
Section | Guidance | Your content
Project name | Short, memorable name used in all communications. | Customer Portal
Purpose / business case | Why the project is needed and the benefits expected. | Reduce account-related support calls by letting customers self-serve.
Objectives (SMART) | Measurable outcomes with dates. | Cut account-related calls by 30% within 6 months of launch.
In scope | What the project will deliver. | Account view, invoices, password reset.
Out of scope | What it will not deliver. | Mobile app; payments.
Key deliverables | Main outputs. | Portal release 1; training guide; support runbook.
Milestones | Major dates. | Design sign-off 15 Feb; Go-live 31 Mar.
Budget | Approved budget or range. | $150,000
Key risks | Top risks known at the start. | Billing system integration delays.
Assumptions and constraints | What you assume to be true and the limits you must work within. | Billing API available by 1 Feb.
Stakeholders | Key people and groups affected. | Customer service, IT, Finance, customers.
Sponsor | Accountable executive. | Head of Customer Service
Project manager and authority | Who leads and what they can decide. | A. Rossi; can approve changes up to $5,000.
Approval | Name, signature and date.

## Revision history
Project Charter Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-charter-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-14 |  | First version created from the template