## Instructions
Product Roadmap Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/product-roadmap-template/
Step | How to use this template
1 | Start from product goals or OKRs, then group work into a few themes.
2 | Add initiatives under each theme and the outcome each should achieve.
3 | Shade the quarters when each initiative is planned.
4 | Assign owners and a confidence level; lower confidence further out is normal.
5 | Review the roadmap monthly and share it with stakeholders.
Tip | Getting the most from it
1 | Focus on outcomes, not feature lists.
2 | Avoid exact dates beyond the next quarter.
3 | Keep a separate release plan for delivery detail.
4 | Use it as a technology or IT roadmap by changing the themes.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Product Roadmap Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/product-roadmap-template/
Total rows with data
Owner | Count | Share
Engineering
Partnerships
Product
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## Roadmap
Product Roadmap Template
Now, next, later: shade the quarters each initiative runs
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/product-roadmap-template/
Theme | Initiative | Goal / outcome | Q1 | Q2 | Q3 | Q4 | Owner | Confidence | Status
Self-service | Customer portal | Cut support calls 30% | ■ | ■ |  |  | Product | High | In progress
Self-service | In-app help centre | Raise CSAT to 8.5 |  | ■ | ■ |  | Product | Medium | Not started
Growth | Partner integrations | 20 new partners |  |  | ■ | ■ | Partnerships | Medium | Not started
Platform | Move to cloud hosting | 99.9% uptime | ■ | ■ | ■ |  | Engineering | High | In progress
Platform | Single sign-on | Enterprise readiness |  |  |  | ■ | Engineering | Low | Not started

## Revision history
Product Roadmap Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/product-roadmap-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-25 |  | First version created from the template