## Instructions
Project Plan Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-plan-template/
Step | How to use this template
1 | Fill in the Overview tab: goal, scope, deliverables, budget and success criteria.
2 | Break the work into phases and tasks on the Project plan tab, using a work breakdown structure.
3 | Give every task one owner, a start date and an end date; the duration calculates automatically.
4 | Record dependencies so you can see which tasks must finish first.
5 | Mark key milestones and agree the plan with your sponsor before work starts.
6 | Update the Status column weekly and use it in your status report.
Tip | Getting the most from it
1 | Plan at a level of detail you can actually keep up to date.
2 | Add buffer to risky tasks rather than padding every estimate.
3 | Keep the plan visible: share the link instead of emailing copies.
4 | Re-baseline only through change control.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Project Plan Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-plan-template/
Total rows with data
Owner | Count | Share
Business analyst
Delivery team
Project manager
Sponsor
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## Project plan
Project Plan Template
Tasks, owners, dates and dependencies
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-plan-template/
ID | Phase | Task / deliverable | Owner | Start | End | Duration (days) | Depends on | Status | Milestone?
1.1 | Initiation | Project charter approved | Sponsor | 2026-01-05 | 2026-01-09 |  |  | Done | Yes
1.2 | Initiation | Stakeholder register | Project manager | 2026-01-07 | 2026-01-12 |  | 1.1 | Done
2.1 | Planning | Requirements workshop | Business analyst | 2026-01-13 | 2026-01-16 |  | 1.2 | In progress
2.2 | Planning | Work breakdown structure | Project manager | 2026-01-19 | 2026-01-21 |  | 2.1 | Not started
2.3 | Planning | Schedule and budget baseline | Project manager | 2026-01-22 | 2026-01-28 |  | 2.2 | Not started | Yes
3.1 | Execution | Build release 1 | Delivery team | 2026-02-02 | 2026-03-13 |  | 2.3 | Not started
4.1 | Closure | Handover and lessons learned | Project manager | 2026-03-16 | 2026-03-20 |  | 3.1 | Not started | Yes

## Overview
Project Plan Template
One-page summary of the plan
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-plan-template/
Item | Details
Project name
Sponsor
Project manager
Goal (SMART) | e.g. Launch the customer portal by 31 March to cut support calls by 30%
In scope
Out of scope
Key deliverables
Budget
Key risks
Success criteria

## Revision history
Project Plan Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-plan-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-26 |  | First version created from the template