## Instructions
Project Deliverables Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-deliverables-template/
Step | How to use this template
1 | List deliverables from the project scope and work breakdown structure.
2 | Describe each in one line and mark it internal or external.
3 | Assign an owner and a due date.
4 | Write clear, testable acceptance criteria and name the approver.
5 | Track status and record approval dates as deliverables are accepted.
Tip | Getting the most from it
1 | Deliverables are nouns: things you can hand over.
2 | Agree acceptance criteria up front to avoid disputes.
3 | Link each deliverable to a milestone.
4 | Keep evidence of sign-off.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Project Deliverables Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-deliverables-template/
Total rows with data
Type | Count | Share
Internal
External
Owner | Count | Share
BA
Design lead
Tech lead
Trainer
Status | Count | Share
Not started
In progress
On hold
Blocked
Done

## Deliverables
Project Deliverables Template
Agree acceptance criteria before work starts
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-deliverables-template/
ID | Deliverable | Description | Type | Owner | Due date | Acceptance criteria | Approver | Status
D1 | Requirements specification | Signed-off business and functional requirements | Internal | BA | 2026-02-13 | Approved by product owner and sponsor | Sponsor | Done
D2 | Design pack | UX designs and technical architecture | Internal | Design lead | 2026-03-06 | Reviewed by architecture board | CTO | In progress
D3 | Portal release 1 | Working portal in production | External | Tech lead | 2026-04-30 | All P1 tests pass; UAT signed | Sponsor | Not started
D4 | Training guide | Guide for support staff | External | Trainer | 2026-04-24 | Reviewed by support manager | Support manager | Not started

## Revision history
Project Deliverables Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/project-deliverables-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-25 |  | First version created from the template