## Instructions
Sprint Retrospective Template: Instructions
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-retrospective-template/
Step | How to use this template
1 | Set the stage: remind everyone of the Sprint Goal and keep it blameless.
2 | Gather observations under Went well, To improve and Ideas.
3 | Vote on the most important items.
4 | Discuss root causes and agree one to three actions with owners on the Action items tab.
5 | Start the next retrospective by reviewing last Sprint's actions.
Tip | Getting the most from it
1 | Change the format occasionally; see retrospective games.
2 | Limit actions so they actually happen.
3 | Add improvement actions to the next Sprint Backlog.
4 | Celebrate wins as well as fixing problems.
Tabs: Dashboard summarises the data automatically; Revision history records changes to this file.

## Dashboard
Sprint Retrospective Template: Dashboard
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-retrospective-template/
Total rows with data
Category | Count | Share
Went well
To improve
Ideas
Shout-outs

## Retrospective
Sprint Retrospective Template
Sprint 14 · 3-16 March
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-retrospective-template/
Category | Observation | Votes | Discussion notes
Went well | Daily Scrums finished on time | 3
Went well | Pairing on the payments story | 4
To improve | Stories arrived in planning without acceptance criteria | 6 | Refine earlier
To improve | Build pipeline failed twice | 5
Ideas | Try a mid-Sprint refinement session | 4
Shout-outs | Thanks to Chen for fixing the test data | 2

## Action items
Sprint Retrospective Template
Pick one to three improvements; review them next retrospective
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-retrospective-template/
Action | Owner | Due | Success measure | Status
Hold a 1-hour refinement session mid-Sprint | Product Owner | 2026-03-25 | All top-10 items have acceptance criteria | Not started
Add pipeline health alert to team channel | Ben | 2026-03-20 | Failures noticed within 10 minutes | Not started

## Revision history
Sprint Retrospective Template: Revision history
Free template by Neural Project Institute · neuralprojectinstitute.com/templates/sprint-retrospective-template/
Version | Date | Author | Summary of changes | Approved by
1.0 | 2026-10-25 |  | First version created from the template